## Pre-Bid Questions
S. No. | Priority | Ask / Remove | Tender Page Ref. | Section / Clause | Tender Point / Clause Description | Clarification | Remarks / Status
1 | High | ASK | Page 1, Page 10, Page 27 | RFQ cover; Section III Annexure-T1; Annexure-C BoQ | Scope says supply/integration of 100 additional SAP ECC 6.0 end-user authorizations; BoQ has Phase-1 quantity as 100 Nos. | Please clarify whether the 100 SAP ECC 6.0 end-user authorizations require fresh SAP license procurement/supply by the bidder, or only configuration/assignment of authorizations within ECIL's existing SAP license pool.
2 | High | ASK | Page 8, Page 9, Page 25, Page 26 | Section II Clauses 6.1 and 6.2; Annexure-A; Annexure-B | EMD of Rs.3,00,000 is required; EMD exemption allowed for MSEs with documentary proof and Bid Security Declaration; MSE certificate must match tender goods/services. | Kindly confirm whether MSE service providers registered under relevant UDYAM IT/software/SAP/technology service categories are eligible for EMD exemption against submission of valid UDYAM certificate, MSE Declaration, and Bid Security Declaration.
3 | High | ASK | Page 11, Page 12 | Section III Detailed Scope of Work; support timing clause | RFQ mentions onsite and offshore model, UAT, user handholding, training, and support team during ECIL working days Monday to Saturday 9:00 AM to 5:30 PM, with late/holiday support if required. | Please confirm the minimum onsite resource requirement, role-wise profile, minimum number of consultants, expected onsite duration, and whether a hybrid onsite/offshore model is acceptable for Phase-1 and Phase-2.
4 | Medium | ASK | Page 12, Page 18, Page 19, Page 20 | Implementation plan; Payment Terms; LD clause | Phase-1 completion is T0+1 month and Phase-2 completion is T0+6 months. Payment clause says 100% payment within 45 days from acceptance. | Please clarify whether payment will be released phase-wise after acceptance of Phase-1 and Phase-2 deliverables, or only after final completion/acceptance of the entire scope.
5 | Medium | ASK | Page 11, Page 12, Page 18, Page 19 | Support obligations; warranty/payment clauses | Scope includes support, training, patches, SAP Notes, user handholding, and 36-month warranty clause is marked not applicable in the table. | Please clarify whether any post-implementation support/AMC period is expected after Phase-2 completion, or whether bidder's support obligation ends after successful completion/acceptance of the 6-month Phase-2 scope.
6 | Medium | ASK | Page 11, Page 12 | Phase-2 integration through SAP PI/PO | RFQ mentions integration of 3rd party application with SAP ECC6.0 through PI/PO using API Integration and Web Services. | Please share/confirm the number and type of third-party applications/interfaces to be integrated, expected API/web-service count, and whether API documentation/test environments will be provided by ECIL.
7 | Medium | ASK | Page 11, Page 12 | SAP landscape and migration/support scope | Scope mentions SAP landscape migration, backups, system refresh/client copy, patches/releases, SAP Notes, and Basis activities. | Please confirm whether SAP landscape migration is part of mandatory bidder scope in this RFQ, and if yes, please specify source/target landscape, systems involved, downtime window, and ECIL/AMC vendor responsibilities.
8 | Low | ASK IF DISCUSSED | Page 24, Page 27 | Evaluation criteria and BoQ | RFQ does not mention estimated project value; BoQ has only quantity, not budget. | Please confirm whether ECIL has an indicative budget/estimated value for this RFQ, or whether bidder should quote purely as per BoQ and scope without any disclosed estimate. | Optional; ask verbally if suitable.