## Pre-Bid Questions
S. No. | Priority | Ask / Remove | Tender Page Ref. | Section / Clause | Tender Point / Clause Description | Clarification | Business Reason | Remarks / Status
1 | High | ASK | Page 1, Page 10, Page 27 | RFQ cover; Section III Annexure-T1; Annexure-C BoQ | Scope says supply/integration of 100 additional SAP ECC 6.0 end-user authorizations; BoQ has Phase-1 quantity as 100 Nos. | Please clarify whether the 100 SAP ECC 6.0 end-user authorizations require fresh SAP license procurement/supply by the bidder, or only configuration/assignment of authorizations within ECIL's existing SAP license pool. | Confirms whether there is any license-selling/resale component or only SAP services/configuration work.
2 | High | ASK | Page 8, Page 9, Page 25, Page 26 | Section II Clauses 6.1 and 6.2; Annexure-A; Annexure-B | EMD of Rs.3,00,000 is required; EMD exemption allowed for MSEs with documentary proof and Bid Security Declaration; MSE certificate must match tender goods/services. | Kindly confirm whether MSE service providers registered under relevant UDYAM IT/software/SAP/technology service categories are eligible for EMD exemption against submission of valid UDYAM certificate, MSE Declaration, and Bid Security Declaration. | Avoids unnecessary EMD payment if Lumbini's MSME/Udyam category is accepted.
3 | High | ASK | Page 11, Page 12 | Section III Detailed Scope of Work; support timing clause | RFQ mentions onsite and offshore model, UAT, user handholding, training, and support team during ECIL working days Monday to Saturday 9:00 AM to 5:30 PM, with late/holiday support if required. | Please confirm the minimum onsite resource requirement, role-wise profile, minimum number of consultants, expected onsite duration, and whether a hybrid onsite/offshore model is acceptable for Phase-1 and Phase-2. | Critical for manpower costing, travel, accommodation, delivery planning, and margin calculation.
4 | Medium | ASK | Page 12, Page 18, Page 19, Page 20 | Implementation plan; Payment Terms; LD clause | Phase-1 completion is T0+1 month and Phase-2 completion is T0+6 months. Payment clause says 100% payment within 45 days from acceptance. | Please clarify whether payment will be released phase-wise after acceptance of Phase-1 and Phase-2 deliverables, or only after final completion/acceptance of the entire scope. | Needed to assess working-capital exposure and billing schedule.
5 | Medium | ASK | Page 11, Page 12, Page 18, Page 19 | Support obligations; warranty/payment clauses | Scope includes support, training, patches, SAP Notes, user handholding, and 36-month warranty clause is marked not applicable in the table. | Please clarify whether any post-implementation support/AMC period is expected after Phase-2 completion, or whether bidder's support obligation ends after successful completion/acceptance of the 6-month Phase-2 scope. | Confirms whether this is a 6-month project only or includes longer support exposure.
6 | Medium | ASK | Page 11, Page 12 | Phase-2 integration through SAP PI/PO | RFQ mentions integration of 3rd party application with SAP ECC6.0 through PI/PO using API Integration and Web Services. | Please share/confirm the number and type of third-party applications/interfaces to be integrated, expected API/web-service count, and whether API documentation/test environments will be provided by ECIL. | Integration effort and risk depend heavily on number and readiness of interfaces.
7 | Medium | ASK | Page 11, Page 12 | SAP landscape and migration/support scope | Scope mentions SAP landscape migration, backups, system refresh/client copy, patches/releases, SAP Notes, and Basis activities. | Please confirm whether SAP landscape migration is part of mandatory bidder scope in this RFQ, and if yes, please specify source/target landscape, systems involved, downtime window, and ECIL/AMC vendor responsibilities. | Prevents under-scoping of Basis/migration effort.
8 | Low | ASK IF DISCUSSED | Page 24, Page 27 | Evaluation criteria and BoQ | RFQ does not mention estimated project value; BoQ has only quantity, not budget. | Please confirm whether ECIL has an indicative budget/estimated value for this RFQ, or whether bidder should quote purely as per BoQ and scope without any disclosed estimate. | Useful for bid/no-bid and pricing strategy; not mandatory to ask formally if sensitive. | Optional; ask verbally if suitable.

## Submission Notes
Field | Details
Tender | ECIL/ITSD/PUR/1100000184 – SAP ECC 6.0 authorizations, integration and support
Pre-bid meeting | 07.05.2026, 10:30 Hrs; RFQ points to physical meeting at ITSD Conference Hall, ECIL Hyderabad.
Should queries be sent in advance? | Yes. Annexure-K says bidders should raise queries in Pre-Bid Query Format only before pre-bid due date.
Recommended submission format | Prepare Annexure-K style table. Send editable Excel + signed PDF on Lumbini letterhead if possible. Carry printed copy to physical pre-bid.
Technical clarification contact | Shri PNV Srinivasa Rao, SDGM (Technical), Tel: 040-27182369, Mobile: 9491696792, Email: pnvsrinu@ecil.co.in
RFQ/commercial contact | Sr. DGM (Purchase), ITSD-Purchase, Direct Line: 040-27182209 / 040-27186261, Email: cmgpur@ecil.co.in
eProcurement portal support | Help Desk: 040-27186294 / 6652 / 2273, Email: etendering@ecil.co.in
Key caution | Do not include financial price in techno-commercial bid. Keep queries limited, precise and clause-linked.
Source pages used | Page 1, 4, 5, 8, 9, 10–12, 18–20, 24, 27, 39, 40.