SECTION 1 — ORGANISATION & TENDER IDENTITY

- Full name of issuing organisation / department: Jaipur Vidyut Vitran Nigam Ltd. (JVVNL / Jaipur Discom)

- Tender number / NIT number / reference number: SE-IT/TN-108 (Tender ID: 2026_JVVNL_554250_1)

- Tender title (exact wording as in document): "Implementation of Feeder Data Monitoring System on System as a Service (SaaS) Basis"

- Procurement type (open / limited / restricted / GeM / QCBS / other): Not mentioned in document.

- Portal / platform where tender is published: https://eproc.rajasthan.gov.in, https://energy.rajasthan.gov.in/jvvnl, https://sppp.rajasthan.gov.in/sppp/

- Tender document fee (amount + payment mode): ₹5,900 total (Tender Fee: ₹2,950 + Processing Fee: ₹2,950). Payment via Demand Draft/Banker's Cheque in favour of "Accounts Officer (IT&RE), Jaipur Discom, Jaipur" (for tender fee) and "MD, RISL" (for processing fee). Online RTGS/NEFT also permitted. MSME (Rajasthan) pays ₹1,475 only.

SECTION 2 — CRITICAL DATES & DEADLINES

| Event | Date | Time | Mode / Location |
| --- | --- | --- | --- |
| Tender document download / sale start date | 24 April 2026 | 09:30 Hrs | Online at e-proc portal |
| Pre-bid query submission deadline | 30 April 2026 | 06:00 PM | Email to seit@jvvnl.org |
| Pre-bid meeting date and time | 01 May 2026 | Not mentioned in document. | Conference Hall, Vidyut Bhawan, Jaipur |
| Bid submission last date and time | 20 May 2026 | 01:00 PM | Online at https://eproc.rajasthan.gov.in |
| Technical bid opening date and time | 22 May 2026 | 03:00 PM | Online at https://eproc.rajasthan.gov.in |
| Financial bid opening date and time | To be intimated later | To be intimated later | To be intimated later |
| Any other milestone dates mentioned in the document | Document Download/Sale End Date | 20 May 2026 | 01:00 PM |
|  | Last date for submission of physical EMD/fees | 21 May 2026 | 03:00 PM in office of AO(M&P-IT), Jaipur |

⚠ AMBIGUITY: The "Document Download/Sale End Date" (20 May 2026, 01:00 PM) and "Bid submission Last Date/Time" (20 May 2026, 01:00 PM) are identical. This may indicate download closes exactly at submission deadline. No explicit "Published Date" is listed in the NIT table, though a "Publishing Date & Time" of 23.04.2026 at 18:00 Hrs appears elsewhere.

SECTION 3 — TENDER VALUE & EMD

- Estimated tender / contract value: ₹51,66,00,000 (Rupees Fifty-One Crore Sixty-Six Lakh Only) inclusive of 18% GST.

- EMD amount (exact figure + currency): ₹1,03,32,000 (2% of estimated value)

- EMD payment mode(s) accepted: Banker's Cheque / Demand Draft in favour of "Accounts Officer (IT&RE), JVVNL" payable at Jaipur; OR Bank Guarantee in favour of "The Superintending Engineer (IT), JVVNL, Jaipur"; OR online RTGS/NEFT.

- EMD exemption clause (MSME / Startup / others — quote exact clause & number):

Clause from NIT table: "In case of small-scale industries of Rajasthan, it shall be 0.5% of the quantity offered for supply and in case of sick industries, other than small scale industries, whose case are pending with Board of Industrial and Financial Reconstruction, it Shall be 1% of the value of bid. Concessional bid security may be taken from register bidders as specified by the State Government."
Also: "Govt. organizations/PSU Companies situated in Rajasthan etc. are exempted from furnishing EMD."

- Performance Bank Guarantee (% of contract value + validity period): 5% of Contract Value. Validity: "six months (6) in addition to the entire contract period."

- Any other security deposit or retention money mentioned: Not mentioned in document. (Retention money is not specified; only Performance Bank Guarantee is required.)

SECTION 4 — CONTACT DETAILS

| Name | Designation | Department | Email | Phone | Full Postal Address | Purpose |
| --- | --- | --- | --- | --- | --- | --- |
| Sh. Rakesh Dusad | Superintending Engineer (IT) | IT, JVVNL | seit@jvvnl.org | 0141-2200972 | 3rd Floor, Data Centre Building, Old Power house, Jaipur-302006 | Tendering Authority / bid queries |
| Not named | Accounts Officer (IT&RE) | IT&RE, JVVNL | aoitre@jvvnl.org | 9414029447 | Not mentioned in document. | EMD / tender fee / payment queries |
| Not named | Helpdesk | eProcurement Cell, RISL | eproc@rajasthan.gov.in | 0141-4022688 | e-Procurement Cell, RISL, Yojana Bhawan, Tilak Marg, C-Scheme, Jaipur | Technical support for e-proc portal |
| Not named | Superintending Engineer (M&P) | O&M / M&P, JVVNL | Not mentioned in document. | Not mentioned in document. | Office of SE(M&P), Jaipur/Bharatpur/Kota (specific address not given) | Invoice verification and execution correspondence |
| Not named | Sr. Accounts Officer (CPC) | CPC, JVVNL | Not mentioned in document. | Not mentioned in document. | Not mentioned in document. | Payment release |

SECTION 5 — PRE-BID INFORMATION

- Is a pre-bid meeting mandatory or optional? Not mentioned in document. (The document states the meeting date but does not specify mandatory/optional.)

- Date, time, and venue / video conference link: 01.05.2026 at Conference Hall, Vidyut Bhawan, Jaipur. Time not mentioned in document.

- Deadline to submit pre-bid queries: 30.04.2026 at 18:00 Hrs

- Mode for submitting queries (email / portal / letter / in-person): Email to seit@jvvnl.org

- Will corrigendum / clarifications be published? On which portal / website?

Clause 5.3: "Any Corrigendum/Addendum issued shall be a part of the Tender document and shall be published on the website of Jaipur Discom & e-proc portal."

- Is site visit required? (date, location, mandatory or optional):

Clause 2.2: "The bidder may in its own interest, before submitting the bid, inspect and examine the area involved and satisfy it regarding the existing system."
Clause 14 (Scope section): "The bidders are presumed to have acquainted themselves with the scope of work of this specification by doing a walk over survey of the area/feeder before submitting their bid."
→ Site visit is not mandatory but strongly recommended. No specific date or location provided.

SECTION 6 — COMPLETE SCOPE OF WORK

6a. Hardware Supply & Installation

- Data Collection and transmission device at substation level:

  - Quantity: Approx. 24,600 points total (Phased: 18,000 Phase-1 + 1,600 Phase-2 + 1,000 Phase-3 + future scalability to 40,000)

  - Memory: 30 days meter data storage

  - Dual communication mode: cellular (GPRS/4G/5G) + secondary (GPRS/RF/other)

  - Power: 110-120V DC / 110-220V AC ±30%, battery backup minimum 2 hours

  - Digital Inputs: Minimum 04 Nos. DI for 4V(DC), 10 mA

  - IP-65 compliant enclosure/box

- Cables and accessories for connecting meters and breakers to data collection device

- Backup Infrastructure at BSDC (Data Center) and DR (Jodhpur): Servers, routers, firewalls, related accessories

- Network equipment for Internet Bandwidth at central location

- OEM / make specifications mentioned: No specific makes or OEMs are mandated.

6b. Software, Licences & Digital Platforms

- Unified web-based application software for data acquisition, aggregation, storage, dissemination, dashboards, graphs, MIS reports

- Mobile application (Android / iOS)

- SMS and email gateway (500-600 SMS per month estimated)

- Network Management System (NMS) for communication network monitoring

- Issue Tracking System (ITS) with ticket management and geo-tagged photo upload

- All required licenses, license updates, renewals, AMC of licenses, software updates to be provided by vendor within quoted price for entire contract duration

- Source code to be handed over to JVVNL at contract termination/completion

- SaaS / cloud platform subscriptions: System to be hosted on vendor-managed infrastructure at BSDC (colocation cost borne by vendor)

6c. Networking, Connectivity & Infrastructure

- GPRS/GSM/4G/5G LTE, NB-IoT, LTE-M, or other suitable IoT communication solutions for field devices

- Redundant bandwidth for high availability

- Connectivity from field to Data Centre via TCP/IP protocol

- Internet connectivity for web applications at hosting level and field level

- Data Centre hosting at Bhamashah State Data Centre (BSDC) – Tier-IV certified – vendor manages servers, networking, storage, application, database, OS

- DR site at Jodhpur with auto failover

6d. Data Migration & Legacy System Integration

- Takeover of existing infrastructure from:

  - M/s Linkwell Telesystems Ltd. (AMR system at approx. 7,500 nos. 11 KV feeder meters)

  - M/s Fox Solutions Pvt Ltd. (DCUs at approx. 4,000 nos. 11 KV outgoing feeders)

- Migration of feeder data from existing Linkwell and Fox systems – migrated data must be frozen and non-editable

- Integration with existing and future JVVNL IT/OT systems including but not limited to:

  - Utility Billing System (UBS)

  - Customer Care System

  - SCADA / Local SCADA under RDSS

  - Smart Metering System (IPDS, NSGM, RDSS)

  - DT Monitoring System

  - Solar Plants under KUSUM scheme

  - RVPN feeder meters

  - Load Forecasting Systems

  - DUET System (Digitization of utilities for energy transition)

  - National Feeder Monitoring System

  - GIS, Outage Management System (OMS), Asset Management System, EVSE

  - Utility Existing App, Peak Load Management, Distributed Response Management System

- Integration through SOA, WS* specifications, web services, XML, SOAP, WSDL, UDDI

- API / interface compliance with open industry standards

6e. Testing, Commissioning & UAT

- Proof of Concept (PoC): Within 60 days from work order for at least 10 Sub Stations

- Demonstration of software before deployment

- Pre-commissioning inspection by JVVNL

- Stabilization Period: 3 months after completion of installation (Phase 2 & 3) – during which system operated under real working conditions, defects rectified, performance ensured

- Operational Go-Live: Within 12 months from work award after successful stabilization

- Independent third-party Cyber security audit required before Operational Go-Live

- Sign-off authority: JVVNL (designated committee for PoC clearance; SE(IT) for Go-Live certificate)

6f. Training

- Training to DISCOM officers for operation and usage of the system

- Training at Circle level to all Engineers from Junior Engineer (J.E.) to Superintending Engineer (S.E.)

- One-time activity, in-depth training at no cost to JVVNL

- Certified trainers from vendor's office

- Training module to be mutually discussed

- Training material: "extensive lecture notes, handouts and other training documents", "Illustrations, Video, and Charts"

- Number of batches / users / duration per batch: Not mentioned in document.

6g. Go-Live Support & Handholding Period

- Handholding support during Stabilization Period (3 months)

- No separate "post-go-live handholding period" explicitly defined beyond stabilization

- Dedicated resources: Not mentioned in document.

6h. Annual Maintenance Contract (AMC) & Ongoing Support

- AMC duration: 5 years (Operation & Maintenance period from Go-Live date) + extendable for further 3 years

- Scope of AMC: Full maintenance of entire system – hardware, software, communication network, manpower

- Support levels: Not explicitly defined; but includes round-the-clock NMS, field maintenance, consumables, spares

- Response and resolution time: Not explicitly defined in document; SLA penalties are based on monthly feeder meter data availability percentage (98%/95%/90% thresholds)

6i. Any Other Deliverables

- Documentation:

  - Function design document

  - Hardware description document

  - Test equipment user document

  - Operation and maintenance document

  - Training documentation

  - Database documentation

  - Test procedures

  - Data requirement sheets

  - Infrastructure installation, layout, GA, BOQ, schematics, internal wiring drawings

  - Cabling details for each site

  - Catalogue of services

  - Inception / FDS report within 30 days of award

  - Detailed project implementation plan (GANTT chart)

- Reports / MIS / dashboards: Energy accounting reports, SAIDI/SAIFI reliability indices, daily/weekly/monthly/user-selectable period reports, graphical dashboard on Rajasthan Map with Geo references, MLA constituency-wise reports, public portal reports

- Regulatory / compliance submissions: Compliance with Make in India, Atmanirbhar Bharat, MeitY circulars, Ministry of Power orders (specific order numbers quoted in document)

- End-of-contract transfer: All infrastructure (hardware, software licenses, source code with documentation, manuals, database, records) to be handed over in working condition

SECTION 7 — COMPLETE ELIGIBILITY CRITERIA

7a. Legal & Registration

- Company / entity types accepted: Company registered in India as per Indian Companies ACT, existing from last 5 financial years (FY 2019-20 to 2024-25). Consortium allowed (max 2 members).

- GST registration, PAN, MCA registration requirements: Valid GSTIN required (copy to be submitted). PAN card copy required. Incorporation Certificate, MOA & AOA required.

- Blacklisting / debarment / litigation conditions:

Clause from QR: "The Bidder should not be backlisted/ debarred by utility/Government agency of all over India, if he has been convicted of an offence: under the Prevention of Corruption Act. 1988 (Central Act no. 49 of 1988) or, Under the Indian Penal Code1860 (Central Act no. 45 of 1860)... In case a Bidder has been blacklisted/debarred for the offences/ground other than enumerated (1) above by any Rajasthan Discom, then the debarment shall be limited to such Discom only and not to others."
Additional clause: "Irrespective of meeting the qualification requirements, none of the consulting companies engaged by Jaipur Discom as on 01.04.2026 for IT Projects can bid for this tender."

7b. Financial Criteria

- Minimum average annual turnover: ₹15 Crores during each of the last three financial years ending on 31-03-2025 (2022-23, 2023-24, 2024-25). Consortium: lead bidder to meet minimum 75% of turnover requirement.

- Net worth requirement: Positive net worth during last three financial year 2022-23, 2023-24, 2024-25. Consortium: lead bidder to meet minimum 75% of net worth requirement.

Definition: "Net worth means the sum total of the paid up capital and free reserves (excluding reserves created out of revaluation) reduced by aggregate value of accumulated losses (including debit balance in profit and loss account for current year) and intangible assets."

- Profitability condition (profit-making for how many consecutive years): Not mentioned in document.

- Any specific revenue from IT / relevant domain required: Not mentioned in document.

7c. Technical & Experience Criteria

- Minimum number of similar completed projects required: Not mentioned in document. (Only "experience of providing System Integration Services" is required.)

- Minimum value per qualifying project (₹ amount): Not mentioned in document.

- Type of client required (Central Govt / State Govt / PSU / private): "Power utilities in India" (from QR clause 2)

- Eligible experience period (e.g., last 5 years / last 7 years): "in last 5 years" (from QR clause 2)

- Definition of "similar work" as stated in the document:

QR clause 2: "System Integration Services involving supply, deployment of Hardware, Software Development & Manpower to power utilities in India in any one of services like Meter Data Downloading & generating Reports, Meter Data Management, Meter Data Acquisition"

7d. Certifications & OEM Partnerships

- OEM authorisation / partnership letter requirements (specify product/brand): Annexure-8 (Manufacturer's Authorization Form) is included in the document template but the document does not explicitly state it is mandatory.

- ISO certifications required (ISO 9001 / ISO 27001 / ISO 20000 / other): "The Lead bidder should be ISO 9001:2015 (Quality Management System)" – valid certificate required.

- CMMI / CMMi-Dev level requirement: Not mentioned in document.

- Technology-specific certifications (SAP Gold / Microsoft Gold / AWS / other): Not mentioned in document.

- Any STQC / CERT-In / GEM / DIPP registration required: Not explicitly mentioned, but compliance with MeitY circular No.1(10)/2017-CLES dated 06.12.2019 (cybersecurity) is required.

7e. Manpower & Key Personnel

- Minimum number of technical / functional staff required: Not mentioned in document. (Scope requires "sufficient manpower for operation, maintenance and Updating" – no specific count.)

- Qualifications and certifications for key roles (Project Manager, Architect, etc.): Not mentioned in document.

- Minimum experience required per role (years): Not mentioned in document.

- Requirement to submit CVs / profiles with bid: Not explicitly mentioned. Annexure-7 (Approach & Methodology) requires "resources with list of man power to be deployed" – but CVs are not explicitly requested.

SECTION 8 — IMPORTANT BIDDING CONDITIONS

- Bid submission mode (online portal / physical / both): Online only through https://eproc.rajasthan.gov.in. Physical submission of original EMD, tender fee DD, and processing fee DD is required after online bid submission, by 21 May 2026, 03:00 PM.

- Number of bid covers / envelopes required: Two parts online – Part A (Technical Bid) with Cover 1 (Fees) and Cover 2 (Techno-Commercial Bid); Part B (Financial Bid).

- Language of bid: English only.

- Bid validity period (days from submission date): 180 days from the date of bid submission deadline. EMD validity: 270 days from date of Bid Submission deadline.

- Mandatory pre-qualification / empanelment condition (if any): Not mentioned in document.

- Make in India / Atmanirbhar Bharat preference clause (if any):

Clause from Section 1, Objective: "The bidder needs to ensure the compliance of guidelines issued in Order No. F/No.6/18/2019-PPD by Ministry of Finance... latest Government of India Guidelines for Make in India, Domestically manufactured products, Atmanirbhar Bharat... including any amendments or modifications to the same from time to time."
→ Preference is stated as a compliance requirement, not an evaluation preference.

- Startup India / MSME preference or reservation (if any): Concessional EMD (0.5% for Rajasthan SSI) and concessional tender fee (₹1,475 for MSME situated in Rajasthan classified under Section 7(1) of MSME Development Act 2006). No other preference mentioned.

- Evaluation method (L1 / QCBS / marks-based / other): L1 – "The bids will be evaluated and awarded as per the evaluation criteria that 'The Bidders having lowest financial quote during Financial Bid Evaluation shall be considered as the L1 Bidders'."

- Minimum technical score required to qualify for financial bid opening: Not mentioned in document. (Evaluation is pass/fail based on QR compliance and "No Deviation" certificate.)

SECTION 9 — CONSORTIUM, JOINT VENTURE & SUBCONTRACTING

- Is consortium / JV / partnership allowed?
→ YES – quote the exact clause and clause number:

Section 2 – Qualification Requirements: "The BIDDERs (Consortium allowed up to maximum of two (2) entities, including the lead bidder) shall be considered responsive only on satisfying the following 'Qualification Requirements'."
Also: "A consortium of maximum two bidders each of the bidders should be a Company registered in India..."
→ Maximum number of members allowed: 2 (Lead Partner + One other partner)
→ Lead member eligibility criteria: Lead bidder must meet minimum 75% of turnover requirement; Lead bidder must meet minimum 75% of net worth requirement; Lead bidder must possess ISO 9001:2015; Lead bidder must possess Class 'A' or 'B' electrical license.
→ Credential / turnover sharing rules between members: Not explicitly defined beyond the 75% lead requirement. QR states "each of the bidders should be a Company... existing from last 5 financial years."

- Is subcontracting allowed?
→ Not explicitly stated. However:

Clause 38: "The Agency shall not assign or transfer the contract or any part thereof to any other agency/ personnel during the contract period."
→ "Assign or transfer" may imply subcontracting is prohibited, but the word "subcontract" does not appear. ⚠ AMBIGUITY: The document does not explicitly say "subcontracting is allowed" or "subcontracting is prohibited." Clause 38 uses "assign or transfer" which may be interpreted differently.

SECTION 10 — PAYMENT TERMS

- Payment milestones (% on which event — delivery / installation / UAT / go-live):

  - Monthly invoice based on actual quantity of feeder meters monitored during calendar month

  - First payment released only after Operational Go-Live certificate

  - 100% of monthly invoice paid after verification and penalty deduction

  - Mobilization advance: 10% of contract value for one year available on request against Bank Guarantee (10% of contract value for one year), recovered in 12 equal monthly installments from first running bill

- Retention money (% withheld + conditions for release): Not mentioned in document. (Only Performance Bank Guarantee is required; no retention money clause found.)

- Invoice processing and payment timeline (days from invoice submission):

  - Invoice submitted within 7th of every month

  - Nodal Officer verifies by 15th of every month

  - Sr. AO (CPC) releases 100% payment within 30 days after receipt of invoices complete in all respects

- Mode of payment (RTGS / NEFT / cheque / LC): Electronic mode (RTGS or NEFT)

- Advance payment (% amount + conditions + bank guarantee required): Mobilization advance – 10% of contract value for one year – against Bank Guarantee of same amount valid for 15 months.

- Tax deduction at source — TDS clause (if mentioned, quote clause): Not explicitly detailed. Clause 6.8.4 mentions Entry Tax deduction but not general TDS.

- GST applicability and who bears the cost: Included in estimated value (₹51.66 Cr inclusive of 18% GST). Clause 6.7.2 states prices should be inclusive of GST. Clause 44: "The Bidder shall furnish details of applicable GST as on date of bidding which shall be paid." Any statutory variation or new tax imposed by government subsequent to bid submission shall be on Discom account.

SECTION 11 — SLA, PENALTIES & PERFORMANCE

- System uptime / availability SLA (% and measurement period):

  - Central Data Center (Servers and Networking): 99.995%

  - All Data Collection and transmission devices and other Field devices: 98%

- Incident priority categories (P1 / P2 / P3 or equivalent) — if defined: Not defined as P1/P2/P3. Instead, penalty is based on monthly feeder meter data availability percentage:

  - ≥98% of total feeders meters of Circle → No penalty

  - Below 98% and up to 95% → No payment towards non-reporting feeders + 10% penalty on unit rate on total number of non-reporting feeders

  - Below 95% and up to 90% → No payment towards non-reporting feeders + 20% penalty on unit rate on total number of non-reporting feeders

  - Below 90% → No payment shall be made

  - Penalty calculated per circle; issues attributable to JVVNL not counted for SLA calculation

- Response time per category: Not mentioned in document.

- Resolution time per category: Not mentioned in document.

- Penalty for SLA breach (% per incident / per hour / per day — exact figure): See above – monthly feeder data availability penalty structure.

- Liquidated damages (LD) for project delay:

  - 0.5% (half percent) per week or part thereof for delay in Operational Go-Live beyond stipulated schedule

  - Maximum cap on LD: 10% (ten percent) of the contract value

  - Thereafter, Nigam reserves right to cancel the contract

- Performance review frequency (monthly / quarterly / annually): Monthly (based on monthly invoice verification and SLA report)

- Termination clause:

  - Termination for cause (conditions):

Clause 6: "If the average meter read provided by the contractor is less than 60% in three consecutive months than JVVNL the contract may be terminated (Except the Stabilization period and force major condition)."
Clause 41: "If the services of the vendor are not as per the awarded work for three consecutive months after commencement of work or non-response after 14 days' notice then Discom will have liberty to terminate the project."

  - Termination for convenience (notice period + compensation):

Clause 24.3: "The Contract can however be otherwise terminated by either party by giving six-month notice and on terms to be mutually agreed which may include payment of suitable compensation for losses suffered by the other party due to such termination."

SECTION 12 — TIMELINE & CONTRACT DURATION

- Implementation / project completion period (from date of work order / LOA): 12 months to Operational Go-Live (from date of work award)

- Phase-wise timeline (if milestones or phases are defined in document):

| S.No | Activity | Timeline (from work order) |
| --- | --- | --- |
| 1 | Furnishing Detailed Road Map | Within 30 days |
| 2 | Submission of Detailed Data Sheet of Software | Within 45 days |
| 3 | Proof of Concept | Within 60 days |
| 4 | Implementation in One Circle (Phase 1 + Hosting on BSDC) | Within 120 days |
| 5 | Completion of Phase 1 (all circles) | Within 180 days |
| 6 | Completion of Phase 2 & Phase 3 | Within 270 days |
| 7 | Stabilization Period | 3 months from completion of Sr.6 |
| 8 | Operational Go-Live | Within 12 months |
| 9 | Operation & Maintenance Period | 5 years from Go-Live |

- Go-live date or target date (if mentioned): Operational Go-Live within 12 months from date of work award.

- Total contract duration (implementation + AMC / O&M period): 6 years (1 year implementation + 5 years O&M) from date of award of contract.

- Contract extension clause (maximum extension period + conditions): Extendable for further 3 years as per mutual agreement.

- Governing law (state / central) and jurisdiction (city / court): Laws of India; exclusive jurisdiction – courts at Jaipur only.

- Dispute resolution mechanism (arbitration / court / mediation):

Clause 29: "In any time, any question, dispute or difference whatsoever which may arise between Jaipur Discom and the Agency, the same shall be decided by CMD/MD of Jaipur Discom, or by the settlement committee constituted by him and shall be final and binding on both the parties."
Settlement committee with fees: CE level (₹1,000), Corporate level (₹3,000), Board of Directors review (₹5,000).
First appeal: Chairman & Managing Director, Rajasthan Vidyut Utpadan Nigam Ltd. Fee: ₹2,500.
Second appeal: Energy Department, Government of Rajasthan. Fee: ₹10,000.

SECTION 13 — RISK FLAGS & GO / NO-GO SUMMARY

13a. Key Risks Identified (maximum 5 — most critical first)

- Unfunded Takeover of Existing Infrastructure: Vendor must take over existing AMR systems (Linkwell, Fox) and replace/upgrade any incompatible components at own cost without any financial implication to DISCOM. This is uncapped financial risk.

- Unlimited Future Scope at Fixed Price: System must scale to 2x feeders (≈40,000) at no additional cost. Any new substation/feeder commissioned during contract must be included at same unit price. Future quantity up to 50% increase in contract value can be imposed with consent of firm.

- End-of-Contract Asset Transfer: All hardware, software, licenses, and source code must be handed over to JVVNL in working condition at contract end. Hardware at BSDC and substations must be transferred with no compensation.

- High Performance Penalty Structure: Payment for a whole circle can be zero if feeder data availability falls below 90% in any month. Penalty applies even if only a small percentage of feeders are non-reporting (e.g., 95-98% range triggers 10% penalty on non-reporting feeders + no payment for those feeders).

- Extremely Short QC / PoC Timelines: PoC (for 10 substations) required within 60 days of work order. Implementation in first circle within 120 days. Tight schedule given the scale (24,600+ points across 15 districts with diverse terrain).

13b. Eligibility Quick-Check (for bid / no-bid decision)

| Criteria | Requirement | Our Status (leave blank) |
| --- | --- | --- |
| Company registration | Registered in India under Companies Act, existing for last 5 FYs (2019-20 to 2024-25) |  |
| Annual turnover (last 3 FYs) | ₹15 Crores minimum per year (2022-23, 2023-24, 2024-25) |  |
| Positive net worth (last 3 FYs) | Positive net worth for 2022-23, 2023-24, 2024-25 |  |
| System Integration experience | With Power Utilities in India for Meter Data Downloading/MDM/Acquisition in last 5 years |  |
| Electrical license | Class 'A' or 'B' from Govt. of Rajasthan (or ₹5 Lakh BG + undertaking to obtain within 2 months of award) |  |
| ISO 9001:2015 | Lead bidder must hold valid certificate |  |
| Consortium (if applicable) | Max 2 members; lead must meet 75% turnover and 75% net worth |  |

13c. Top 5 Clarifications to Raise in Pre-Bid Meeting

- Takeover of Existing Infrastructure (Linkwell & Fox): What is the approximate age and condition of the existing DCUs, modems, and software licenses? Is there any documented inventory or assessment report available? What is JVVNL's estimate of the percentage likely to require replacement at vendor's cost?

- Scalability to 2x Feeders (≈40,000 points): Is the "2x" requirement based on the current 24,600 count or on the final deployed count after Phase 3? What is the process and timeline for notifying vendor of new feeders requiring installation?

- Definition of "Assign or Transfer" (Clause 38): Does this clause prohibit subcontracting of specific components (e.g., field installation, cabling, manpower supply)? If subcontracting is allowed for non-core activities, what approval process and percentage limits apply?

- Payment Start Date Clarification: The document states "first payment shall be released only after operational Go-Live (12 months)". However, mobilization advance (10%) is available. Does JVVNL confirm that no monthly recurring payments will be made during the 12-month implementation period even for feeders that are commissioned and reporting earlier?

- Force Majeure – Data Protocol Delays: The document notes that for proprietary/non-DLMS meters, DISCOM will replace the meter. If DISCOM delays meter replacement, will the 12-month Go-Live deadline be extended under the Force Majeure exception clause (Clause 26.4.1 – "Non-availability / delay in readiness of site infrastructure not attributable to bidder")?

▶ EXECUTIVE SUMMARY

Jaipur Vidyut Vitran Nigam Limited (JVVNL) has issued tender TN-108 for implementation of a unified Feeder Data Monitoring System on a SaaS basis across 15 districts of Rajasthan. The estimated tender value is ₹51.66 crore inclusive of GST. Key submission deadline is 20 May 2026 (01:00 PM) with technical bids opening on 22 May 2026. EMD required is ₹1.03 crore (2% of estimated value). The critical eligibility requirement is that the lead bidder must have System Integration experience with Indian power utilities in meter data management within the last 5 years, along with minimum ₹15 crore annual turnover for the last three financial years and positive net worth. Consortiums of up to two members are permitted, with the lead member meeting 75% of financial criteria. Vendors should note significant financial risks including mandatory takeover of existing infrastructure at vendor's cost and unlimited future feeder additions at fixed pricing over the 6-year initial contract term (extendable by 3 years).