Tender Analysis Summary: JVVNL Feeder Data Monitoring System (SaaS) Rajasthan

Document Reference: TN-108 / 2026_JVVNL_554250_1
Issuing Authority: Jaipur Vidyut Vitran Nigam Ltd. (JVVNL)

1. Organization Name & 2. Tender Number

- Organization Name: Jaipur Vidyut Vitran Nigam Ltd. (JVVNL / Jaipur Discom)

- Tender Reference Number: SE-IT/TN-108

- Tender ID: 2026_JVVNL_554250_1

- Estimated Tender Value - ₹51,66,00,000 (Rupees Fifty-One Crore Sixty-Six Lakh Only)

3. Last Date of Bid Submission (with time)

| Event | Date & Time |
| --- | --- |
| Bid Submission End Date/Time | 20 May 2026, 01:00 PM |
| Bid Submission Start Date | 15 May 2026, 01:00 PM |
| Technical Bid Opening Date | 22 May 2026, 03:00 PM |
| Financial Bid Opening Date | To be intimated later |

4. Contact Details

| Role | Name / Designation | Contact Info |
| --- | --- | --- |
| Tendering Authority | Superintending Engineer (IT), JVVNL | Address: 3rd Floor, Data Centre Building, Old Power House, Banipark, Jaipur-302006 Phone: 0141-2200972, 9413390182 Email: seit@jvvnl.org |
| Nodal Officer (Payments) | Accounts Officer (IT&RE) | Email: aoitre@jvvnl.org Phone: 9414029447 |
| e-Procurement Helpdesk | RISL | Phone: 0141-4022688 Email: eproc@rajasthan.gov.in |

5. Pre-Bid Information

| Item | Details |
| --- | --- |
| Pre-bid Meeting Date | 01 May 2026 |
| Pre-bid Meeting Mode/Location | Conference Hall, Vidyut Bhawan, Jaipur (Physical Meeting) |
| Query Submission Deadline | 30 April 2026, 06:00 PM |
| Query Submission Mode | Via email to seit@jvvnl.org |

6. EMD Details

| Item | Details |
| --- | --- |
| EMD Amount | ₹1,03,32,000 (2% of estimated project value of ₹51.66 Cr) |
| Mode of Payment | Banker’s Cheque / Demand Draft / Bank Guarantee in favour of "Accounts Officer (IT&RE), JVVNL" payable at Jaipur. Online RTGS/NEFT also permitted. |
| Exemption Clause | Yes, as per RTPP Act/Rules: • SSI of Rajasthan: 0.5% (₹25.83 Lakhs) • Sick Industries (BIFR): 1% (₹51.16 Lakhs) • State Govt. Depts/Undertakings: Exempted (Bid Securing Declaration required) |

7. Complete Scope of Work (Breakdown)

| Section | Scope Details |
| --- | --- |
| Services (SaaS Model) | Implementation of a unified, web-based Feeder Data Monitoring System on a System as a Service (SaaS) basis for 6 years (1 year implementation + 5 years O&M). |
| Hardware (Field) | Supply, install, and maintain Data Collection & Transmission devices, cabling, enclosures (IP-65), and dual-mode communication (GPRS/4G/5G + secondary) at ~24,600 points (11kV, 33kV, VCBs, boundary points). |
| Hardware (Central) | Procure and manage IT infrastructure (servers, network, security) hosted at Bhamashah State Data Centre (BSDC) and DR site (Jodhpur) at vendor's cost. |
| Software | Design, develop, and deploy a web-based application with dashboards, MIS reports, energy accounting, SAIDI/SAIFI, query builder, mobile app, and public portal. Must be SOA-based. |
| Integration | Integrate with existing systems (Linkwell, Fox Solutions AMR), UBS, SCADA, GIS, RDSS, Smart Metering, KUSUM, RVPN, National Feeder Monitoring System, DUET, etc. |
| Data Migration | Migrate historical data from existing Linkwell & Fox systems. Migrated data must be frozen and non-editable. |
| Takeover of Existing Assets | Take over existing DCUs, modems, software licenses, and accessories from M/s Fox Solutions and M/s Linkwell without any cost to JVVNL. Replace/upgrade incompatible components at vendor's own cost. |
| Support & Maintenance | Provide 5 years of O&M post Go-Live, including manpower, consumables, spares, SIM/eSIM, SMS gateway, training, and 24/7 Network Management System (NMS). |
| End-of-Contract Transfer | Transfer all infrastructure (hardware, software licenses, source code, documentation) in working condition to JVVNL at the end of the contract period. |

8. Complete Eligibility Criteria

Technical Criteria

| # | Requirement | Evidence Required |
| --- | --- | --- |
| 1 | Bidder must be a company registered in India under Companies Act, existing for last 5 FYs (2019-20 to 2024-25). | Incorporation Certificate, MOA & AOA. |
| 2 | Consortium allowed? YES (Max 2 members, including Lead Bidder). | Registered Consortium Agreement with joint & several liability clause. |
| 3 | Lead bidder must have System Integration experience with Power Utilities in India (Meter Data Downloading, MDM, or Acquisition) in last 5 years. | Work Orders & Performance Certificates. |
| 4 | Lead bidder must hold ISO 9001:2015 certification. | Valid ISO Certificate. |
| 5 | Bidder must have Class 'A' or 'B' electrical contract license from Govt. of Rajasthan (OR furnish ₹5 Lakh BG and undertaking to obtain it within 2 months of award). | License copy OR BG + Undertaking. |
| 6 | Bidder must not be blacklisted/debarred for specific corruption/penal code offenses. | Annexure-12 (Self Declaration on stamp paper). |

Financial Criteria

| # | Requirement | Evidence Required |
| --- | --- | --- |
| 1 | Lead bidder min. annual turnover: ₹15 Crores in each of last 3 FYS (2022-23, 2023-24, 2024-25). Consortium: Lead must meet 75% of this. | Audited P&L, Balance Sheet, CA Certificate with UDIN. |
| 2 | Bidder must have positive net worth in last 3 FYs (2022-23, 2023-24, 2024-25). Consortium: Lead must meet 75%. | Audited statements with CA certificate. |
| 3 | Valid GSTIN required. | Copy of GST Registration. |

Other Requirements

- OEM/Partnership: Not explicitly required as a separate clause, but implied for hardware/software being proposed (Bill of Materials to be submitted).

- Note: Consulting companies engaged by JVVNL for IT projects as of 01.04.2026 cannot bid.

9. Important Conditions for Bidding

| Category | Details |
| --- | --- |
| Payment Terms | • Monthly invoicing by 7th of each month. • Nodal officer verifies by 15th. • 100% payment within 30 days of verification (after deducting penalties). • First payment only after "Operational Go-Live". • Mobilization Advance: 10% of 1st year contract value available against 15-month BG. |
| SLA / Penalties | • Implementation Delay: 0.5% per week (max 10% of contract value). • O&M Penalty (Circle-wise): - ≥98% uptime: No penalty. - 95% to <98%: No payment for non-reporting feeders + 10% penalty. - 90% to <95%: No payment + 20% penalty. - <90%: No payment for the month. |
| Performance Guarantee | 5% of Contract Value (valid for contract period + 6 months). To be submitted within 15 days of Work Order. |
| Submission Mode | Online only via https://eproc.rajasthan.gov.in using Digital Signature Certificate (DSC Type II/III). Physical copies of EMD/fee receipts must be submitted after online deadline. |
| Restrictions | • Consortium allowed (max 2 members). • No subcontracting explicitly allowed (clause 38: "Agency shall not assign or transfer the contract or any part thereof"). |

10. Any Other Important Information

- Consortium is NOT allowed? INCORRECT. Consortium is explicitly ALLOWED (max of two entities, including lead bidder). (Refer to Section 2: Qualification Requirements & Note 2)

- Project Timeline (Implementation Schedule)

  - Detailed Roadmap: Within 30 days of award

  - Proof of Concept (PoC): Within 60 days of work order

  - Phase 1 (11kV & 36kV VCBs) Completion: Within 180 days

  - Phase 2 & 3 (33kV & Boundary) Completion: Within 270 days

  - Stabilization Period: 3 months

  - Operational Go-Live: Within 12 months of work award

  - O&M Period: 5 years from Go-Live

- Contract Duration

  - Initial term: 6 years (1 year implementation + 5 years O&M) from date of work order.

  - Extendable: For a further 3 years by mutual agreement.

- Special Clauses & Risks

  - SaaS Model with Asset Transfer: Entire infrastructure (including BSDC-hosted hardware) and source code must be transferred to JVVNL at contract end.

  - Unlimited Scalability Risk: System must scale to 2x feeders (≈40,000) at no extra cost. Future feeders added during contract must be included at same unit price.

  - Integration Responsibility: Vendor bears full cost and risk of integrating with multiple existing/future JVVNL IT/OT systems and government platforms.

  - Fall Back Arrangement: JVVNL can take over all systems and recover losses from BGs if vendor fails.

  - Force Majeure: Defined but strikes/lockouts beyond 7 days allow JVVNL to procure elsewhere at vendor's risk.